## Plan
Drive Safe
Company name | Team 3 |  |  |  | Legend: | G |  |  |  |  | SB |  |  |  |  | B |  |  |  |  | P |  |  |  |  | Unassigned
Project lead | Saif Javed
Project Start Date: | 2021-01-26 |  |  |  |  | January | [6 empty] | February | [27 empty] | March
Scrolling Increment: | 1 | time axis 2021-01-27 to 2021-03-23
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2021-01-27 to 2021-03-23
Project General Phases
Team Building | Milestone | All | 100% | 2021-01-26 | 7 | bar: 2021-01-27 to 2021-02-01
Problem Statement | On Track | All | 100% | 2021-02-02 | 7
Aims and Objectives | Low Risk | All | 50% | 2021-02-02 | 10
Data Selection | Med Risk | All | 100% | 2021-02-02 | 10
Requirments Definition | High Risk | All | 50% | 2021-02-09 | 7
Methodology | On Track | All | 10% | 2021-02-16 | 7
System Design | Low Risk | All | 0% | 2021-02-16 | 7
Implementation phase 1 (M1) + prototype | Milestone | All | 0% | 2021-02-23 | 10 | bar: 2021-02-23 to 2021-03-04
Implementation phase 2 | High Risk | All | 0% | 2021-03-05 | 22
Test the system Aginst the Reqs | On Track | All | 0% | 2021-04-19 | 5
Quality Assurance Testing & evaluvation (M2) + system | Low Risk | All | 0% | 2021-04-24 | 5
System Deployment | Goal | All | 0% | 2021-04-29 | 5
Detailed Tasks
Task 1 | On Track |  |  | 2021-03-01 | 0
Task 2 | Med Risk |  |  | 2021-03-02 | 0
Task 3 | On Track |  |  | 2021-03-03 | 0
Task 4 | Goal |  |  | 2021-03-04 | 0
Task 5 | Low Risk |  |  | 2021-03-05 | 0
Task 6 | Low Risk |  |  | 2021-03-06 | 0
Task 1 |  |  |  | 2021-03-07 | 0
Task 2 |  |  |  | 2021-03-08 | 0
Task 3 | Milestone |  |  | 2021-03-09 | 0
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Sheet1
project phases | Project Plan
Problem Statement | Problem Statement
Aims and objectives | Aims and objectives
Data Selection | Data Selection
Requirments | Requirments
Methodology | Methodology
System Design | System Design
Implementation phase 1 (M1) + prototype | Understand and analyze the data
Implementation phase 2 | Visualize the data
Test the system aginst the req | Train and test data
Quality Assurance Testing & evaluvation (M2) + system | Verify prediction results
Quality Assurance Testing & Evaluation